## Sheet1
Hypercontext - Meeting agenda template
Jira's Sprint Planning Meeting
----------
Description: Sprint Planning meetings are a critical part of the development process. This meeting template from Atlassian Jira's agile coaches, should keep everything on track. In the Sprint Planning meeting, the Scrum Master sets the stage by presenting relevant action items from the retrospective. Next, the product owner sets the tone from above by providing product or market updates. Following the debriefs, the product owner starts the actual planning conversation, by working with the development team to set a sprint goal and the work that will ensure the goal is met.
Date: Feb 11th
----------
Agenda:
RETROSPECTIVE RECAP (5-10MIN)
1 .[Scrum Master] Discuss relevant action items from the retrospective
PRODUCT AND MARKETING UPDATES (5-10MIN)
2 .[Product Owner] shares context around product and market updates
PLANNING CONVERSATION (45-60MIN)
3 .Set the Sprint Goal
4 .Confirm Velocity for team (Average Velocity, Team capacity, etc)
5 .Walk through of stories suggested for the sprint. Discuss work required for each.
RECAP & CONFIRM (5-10MIN)
6 .What each person is shipping by the end of the sprint?
7 .What each person is starting on?
This template was generated by Hypercontext.com
With Hypercontext, every meeting has a shared goal, agenda, notes, and next steps.